## Hoja1
These are the taks delivered to create The Cliffborn Islands
| Task |  | Estimated time | Real time | Date of delivery
Oscar Faura | Player 1 & Player 2 controlling |  | 3h | 20h | 2018-06-05
| Fixed bugs |  | 2h | 5h | 2018-06-05
| implemented few enemies |  | 4h | 8h | 2018-06-25
| Respawn invulnerability |  | 30min | 30min | 2018-05-10
| Added wall colliders |  | 2h | 4h | 2018-05-06
| Fixed laser type |  | 30min | 30min | 2018-05-05
Dani Lorenzo | Implemented most of the basic enemies |  | 25 h | 40 h | 20/05/0218
| Implementing the whole Boss |  | 6h | 12h | 2018-06-05
| Implementing issues. templates and milestones |  | 1h | 30 minutes | 2018-05-04
|  | TOTAL | 32h | 52.5h aprox

## Hoja2
These are the taks delivered to create The Cliffborn Islands
| Task | Estimated time | Real time | Delivery date
Oscar Faura
Dani Lorenzo | Creating the repositoty and implementing the license | 15 minutes | 10 minutes | 2018-10-05
| Creating the map of lvl2 with it's colliders | 2h | 3h | 2018-10-13
| Implementing the player module with all its animations | 1h | 1h | 2018-10-07
| Implementing the movement and the jump of the player | 1h | 2h 30 minutes | 2018-10-08